## Sheet1
ID | Task | Description | Duration(H) | Start Date | End Date | Priority | Status | Actual Start Date | Actual End Date
T1 | Requirements Analysis | Gather requirements and define project scope | 2 Hours | Day 1 | Day 1 | High | Completed | 2026-08-13 | 2026-08-13
T2 | ER Diagram, Relational Schema, User Stories | Design ER diagram, Design relational schema, Write user stories | 5 Hours | Day 1 | Day 1 | High | Completed | 2026-08-13 | 2026-08-13
T3 | Auth0 Setup | Configure Auth0 tenant, API, and SPA application | 2 Hours | Day 2 | Day 2 | High | Not started
T4 | Project Setup | Setup React and .NET Clean Architecture projects | 3 Hours | Day 2 | Day 2 | High | Not started
T5 | Database Setup | PostgreSQL + Dapper repositories | 3 Hours | Day 2 | Day 2 | High | Not started
T6 | Backend Auth | Implement Auth0 JWT validation and user synchronization | 4 Hours | Day 3 | Day 3 | High | Not started
T7 | Frontend Auth | Configure Auth0Provider, login/logout and token attachment | 4 Hours | Day 3 | Day 3 | High | Not started
T8 | Product & Category CRUD | Implement backend CRUD APIs | 6 Hours | Day 4 | Day 4 | High | Not started
T9 | Product Browsing | Develop product browsing and search UI | 6 Hours | Day 5 | Day 5 | Medium | Not started
T10 | Cart Backend | Implement add/update/remove cart logic | 6 Hours | Day 5 | Day 6 | High | Not started
T11 | Cart UI | Implement cart page, badge and totals | 6 Hours | Day 6 | Day 6 | Medium | Not started
T12 | Order Logic | Stock validation and order snapshotting | 5 Hours | Day 6 | Day 7 | High | Not started
T13 | Cart Checkout | Checkout endpoint and frontend | 4 Hours | Day 7 | Day 7 | High | Not started
T14 | Buy Now | Implement Buy Now endpoint and product page UI | 3 Hours | Day 7 | Day 7 | Medium | Not started
T15 | Order History | Develop order history page | 4 Hours | Day 8 | Day 8 | Medium | Not started
T16 | Unit Testing | Write xUnit and Vitest test cases | 8 Hours | Day 8 | Day 9 | High | Not started
T17 | Polish & Demo | Bug fixing, UI polish and demo preparation | 3 Hours | Day 9 | Day 9 | Low | Not started